## Roles and Responsibilities
SALISBURY UNIVERSITY SPONSORED PROGRAM ROLES & RESPONSIBILITIES | Principal Investigator | Department Chair | Dean or VP | School Admin |  | Office of Sponsored Projects |  | Admin and Finance | Dean of GSR | Provost
[5 empty] | DIR. | PRE | POST
PROPOSAL PREPARATION
Search for opportunities | x | x | x |  | x | x |  |  | x
Provide guidance on funding opportunities |  | x | x |  | x | x
Write technical narrative | x
Identify subcontractors and request budget and workscope materials | x |  |  |  |  | x
Requesting/Approving course release or download time | x | x | x
Develop budget | x |  | x |  |  | x
Identify need for cost sharing funds | x |  |  |  |  | x
Evaluate requests for F&A waivers or reductions |  |  | x |  | x |  |  |  | x
Coordinate space arrangements |  | x | x
Provide expert guidance on proposal preparation |  |  |  |  | x | x
Coordinate completion of the proposal routing form | x |  |  |  |  | x
REGULATORY REQUIREMENTS
Complete compliance forms: Institutional Review Board, Animal Care and Use, Dept of Health & Safety | x
Complete conflict of interest disclosure | x
Review conflict of interest disclosure form and facilitate institutional oversight |  |  |  |  | x |  |  |  | x
Ensure all IRB, IACUC applications submitted and under review | x |  |  |  | x | x
PROPOSAL REVIEW AND APPROVAL
Confirm that proposal meets sponsor requirements | x |  |  |  |  | x
Review proposal before sending to Research Office | x
Verify that cost sharing in proposal in listed in KUALI for routing | x |  |  |  |  | x
Review proposed cost sharing for appropriateness | x | x |  |  | x
Review and approval of proposal in KUALI | x | x | x |  | x |  |  |  |  | x⁰
PROPOSAL SUBMISSION
Send proposal to sponsors after institutional approval | [5 empty] | x
AWARD ACCEPTANCE (Official acceptance by the University)
Accept sponsor notification of grant or contract award |  |  |  |  | x |  |  |  | x
Review contractual terms and conditions with PI | x |  |  |  | x |  | x
Negotiate sponsor requests for budget and/or scope modifications | x | x | x |  | x | x
Negotiate contractual terms and conditions with sponsor - secure legal review as needed |  |  |  |  | x |  |  |  | x | x
Approve award terms and conditions |  |  |  |  | x |  |  |  |  | x
Review subcontract/subaward documents - secure legal review as needed | x |  |  |  | x | x
Signature authority of contracts | [9 empty] | x
AWARD SET-UP
Identify need for pre-award or advance project | x | x | x |  | x |  | x
Request pre-award or advance project | x | x | x
Confirm that all regulatory compliance requirements have been met | [6 empty] | x
Modify proposed budget | x |  |  |  |  | x
Prepare award summary documents | [6 empty] | x
Create Grant Account in Workday |  |  |  |  | x
Initial meeting regarding managing sponsored project (purchasing, travel, HR, etc.) | x |  |  | x | x |  | x
CONDUCTING THE PROJECT - FINANCIAL
Initiate purchases | x |  |  | x
Prepare Employment Contracts |  |  |  | x
Prepare financial transactions (POs, Sole Source, etc.) | [6 empty] | x
Process and complete financial, procurement and employment transactions | [7 empty] | x
Initiate re-budget requests | x | [5 empty] | x
Approve and submit re-budget requests¹ | x¹ | [5 empty] | x
Initiate no-cost extensions | x | [5 empty] | x
Approve no-cost extensions (or forward to Sponsor)¹ | x¹ |  |  |  | x |  | x
Update Workday to reflect revised budget and/or time extensions |  |  |  |  | x
Ensure that cost sharing is documented | x | [5 empty] | x
Review and approve expense transactions | [6 empty] | x
Use financial reports to monitor and oversee expenditures | x | [5 empty] | x
Reconcile accounts on a regular basis and distribute to PIs and Deans | [6 empty] | x
Coordinate resolution of issues on oversight reports | [6 empty] | x
PROGRAM INCOME
Identify program income | x |  |  |  |  | x | x
Receive and reconcile program income (registrations). Submit information to Cashier's office. | x |  |  | x |  |  | x
Apply to appropriate project and deposit | x | [5 empty] | x | x
Identify use and reportability of program income | x | [5 empty] | x
Monitor program income levels | x | [5 empty] | x
INVOICING AND FINANCIAL REPORTING
Prepare invoice in Workday | [6 empty] | x
Create and submit invoice to sponsor | [6 empty] | x
Prepare and submit financial reports | [6 empty] | x
ACCOUNTS RECEIVABLE MANAGEMENT
Receive and deposit payments from sponsors | [7 empty] | x
Produce and record a letter of credit draw request (federal awards) |  |  |  |  | x |  | x
Monitor and pursue the collections of overdue payments from sponsors |  |  |  |  | x |  | x
CONDUCTING THE PROJECT - GENERAL
Review and approve incoming Material Transfer Agreements -- secure legal review as needed. |  |  |  |  | x |  |  |  | x | x
Complete invention disclosure form | x
Ensure integrity of notebooks and data | x
PRIOR APPROVALS
Initiate prior approvals for changes to projects | x | [5 empty] | x
Approve or forward to Sponsor prior approvals for changes to project | [6 empty] | x
Ensure regulatory compliance offices are notified of changes to project | [6 empty] | x
SUBCONTRACT AND SUBAWARDS
Oversee scientific aspects of subcontract/subaward | x
Prepare, negotiate, and sign subcontracts/subawards |  |  |  |  | x | x |  |  |  | x
Review and approve subcontract invoices | x | [5 empty] | x
Subrecipient monitoring |  |  |  |  | x |  | x
TECHNICAL/SCIENTIFIC (NON-FINANCIAL) REPORTS
Prepare and submit progress reports to sponsor | x
Maintain the official copy of the progress report | x
PERSONNEL AND EFFORT CERTIFICATION
Initiate hiring process | x |  |  | x |  |  | x
Payroll Certification | x | [5 empty] | x
Complete necessary adjustments to award charges and/or payroll distribution |  |  |  | x |  |  | x
Obtain necessary supervisory reviews and approvals |  |  |  |  | x |  | x
Ensure accurace of costing allocations in Workday | x |  |  |  | x |  | x
PROJECT END AND CLOSEOUT
Identify early close-out situations | x |  |  | x |  |  | x
Ensure all appropriate expenditures have been posted to projects | x |  |  | x |  |  | x
Prepare final financial invoice/report | [6 empty] | x
Approve final financial invoice/report | x |  |  |  | x
Resolve issues related to unreconciled accounts | [6 empty] | x
Ensure that all financial reports have been submitted to sponsor |  |  |  |  | x |  | x
Ensure that all final invention reports have been submitted to sponsor | x | [5 empty] | x
Ensure that the final scientific report and data sharing requirements have been met and submitted. | x
Ensure that all patent reports have been submitted to sponsor | x |  |  |  | x |  |  |  | x
Mark Award as Closeout in Progress in Workday | [6 empty] | x | x
Maintain official project documents for sponsored projects (Sponsor correspondence, financial reports) | [6 empty] | x
A-133 AUDIT
Coordinate the Single audit for the entire University | [7 empty] | x
ONGOING TRAINING
Provide training to the research community regarding changes to policies and regulations |  |  |  |  | x | x | x |  | x
NOTES:
⁰ Approval required by Provost for proposals over $10,000.
¹ Any correspondence between PI and Sponsor should include Research Office